## Hoja 1
| FP | EFFORT | WORKING DAYS |  |  | Phase | % - Phase
Team management SB | 91 | 106.759 | 122.789 |  |  | Requirements Analysis | 20% |  | System analyst | 400 euros/day
Meeting scheduling SB | 14 | 17.3797 | 18.891 |  |  | Design | 20% |  | Senior designer | 350 euros/day
Meeting management SB | 136 | 168.8283 | 183.509 |  |  | Coding | 20% |  | Junior designer | 200 euros/day
Meeting tool SB | 21 | 26.0691 | 28.336 |  |  | Unit testing | 10% |  | Junior designer | 200 euros/day
Statics management SB | 38 | 47.173 | 51.275 |  |  | Integration Testing | 20% |  | System technician | 300 euros/day
TOTAL | 300 | 366.2091 | 404.8 |  |  | Installation | 10%
|  | AFP/(FP/WD) |  |  |  | Total | 100%
| TM | MS | MM | MT | SM
UFP | 91 | 14 | 136 | 21 | 38
AFP | 83.72 | 12.88 | 125.12 | 19.32 | 34.96
INCR-1 SUBSYSTEMS | FP WORKING DAYS |  |  |  |  | 134.934 |  | %-PHASE | %-ACTIVITY | WORKING DAY-PHASE | WORKING DAY-ACTIVITY | RESOURCES | WORKING DAYS
Team Management SB | 86 | 122.789 | 86.6664 | % |  | Analysis |  | 20 |  | 28.2
Meeting Scheduling SB | 14 | 18.891 | 13.3336 | % |  |  | Req.Specification |  | 70 |  | 19.74
TOTAL | 100 | 141.68 | 100 | % |  |  | Prototyping |  | 30 |  | 8.46
Rev. Analysis
[6 empty] | Design |  | 20 |  | 28.2
INCR-2 SUBSYSTEMS | [6 empty] | D.Sub1 |  | 86 |  | 24.252
Meeting Management Subsystem SB | 136 | 183.509 | 100 | % |  |  | D.Sub2 |  | 14 |  | 3.948
TOTAL | 136 | 183.509 | 100 | % |  |  | Rev.Design
[6 empty] | Coding |  | 20 |  | 28.2
[7 empty] | C.Sub1 |  | 86 |  | 24.252
INCR-3 SUBSYSTEMS | [6 empty] | C.sSub2 |  | 14 |  | 3.948
Meeting tool Subsystem SB | 21 | 28.336 | 35.5931 | % |  | Unit Testing |  | 10 |  | 15.1
Statistics Management SB | 38 | 51.275 | 64.4069 | % |  |  | UT-Sub1 |  | 86 |  | 12.986
TOTAL | 59 | 79.611 | 100 | % |  |  | UT-Sub2 |  | 14 |  | 2.114
[6 empty] | Integration Testing |  | 20 |  | 28.2
[7 empty] | Int.Task |  | 86 |  | 24.252
[7 empty] | Rev.Integration |  | 14 |  | 3.948
[6 empty] | Installation |  | 10 |  | 14.1
[7 empty] | Technical Instalation |  | 70 |  | 9.87
[7 empty] | Acceptance |  | 30 |  | 4.23
Rev.Installation
141
[10 empty] | %ACTIVITYxTOTAL | %ACTIVITYx%-TASKxTOTAL
[6 empty] | 183.509 |  | %-PHASE | %-ACTIVITY | WORKING DAY-PHASE | WORKING DAY-ACTIVITY | RESOURCES | WORKING DAYS
[6 empty] | Analysis |  | 20 |  | 36.8
[7 empty] | Req.Specification |  | 70 |  | 25.76
[7 empty] | Prototyping |  | 30 |  | 11.04
Rev. Analysis
[6 empty] | Design |  | 20 |  | 36.8
[7 empty] | D.Sub1 |  | 60 |  | 22.08
[7 empty] | D.Sub2 |  | 40 |  | 14.72
Rev.Design
[6 empty] | Coding |  | 20 |  | 36.8
[7 empty] | C.Sub1 |  | 60 |  | 22.08
[7 empty] | C.sSub2 |  | 40 |  | 14.72
[6 empty] | Unit Testing |  | 10 |  | 18.4
[7 empty] | UT-Sub1 |  | 60 |  | 11.04
[7 empty] | UT-Sub2 |  | 40 |  | 7.36
[6 empty] | Integration Testing |  | 20 |  | 36.8
[7 empty] | Int.Task |  | 60 |  | 22.08
[7 empty] | Rev.Integration |  | 40 |  | 14.72
[6 empty] | Installation |  | 10 |  | 18.4
[7 empty] | Technical Instalation |  | 60 |  | 11.04
[7 empty] | Acceptance |  | 40 |  | 7.36
Rev.Installation
184
[10 empty] | %ACTIVITYxTOTAL | %ACTIVITYx%-TASKxTOTAL
[6 empty] | 79.611 |  | %-PHASE | %-ACTIVITY | WORKING DAY-PHASE | WORKING DAY-ACTIVITY | RESOURCES | WORKING DAYS
[6 empty] | Analysis |  | 20 |  | 16
[7 empty] | Req.Specification |  | 70 |  | 11.2
[7 empty] | Prototyping |  | 30 |  | 4.8
Rev. Analysis
[6 empty] | Design |  | 20 |  | 16
[7 empty] | D.Sub1 |  | 36 |  | 5.76
[7 empty] | D.Sub2 |  | 64 |  | 10.24
Rev.Design
[6 empty] | Coding |  | 20 |  | 16
[7 empty] | C.Sub1 |  | 36 |  | 5.76
[7 empty] | C.sSub2 |  | 64 |  | 10.24
[6 empty] | Unit Testing |  | 10 |  | 8
[7 empty] | UT-Sub1 |  | 36 |  | 2.88
[7 empty] | UT-Sub2 |  | 64 |  | 5.12
[6 empty] | Integration Testing |  | 20 |  | 16
[7 empty] | Int.Task |  | 36 |  | 5.76
[7 empty] | Rev.Integration |  | 64 |  | 10.24
[6 empty] | Installation |  | 10 |  | 8
[7 empty] | Technical Instalation |  | 70 |  | 5.6
[7 empty] | Acceptance |  | 30 |  | 2.4
Rev.Installation
80
[10 empty] | %ACTIVITYxTOTAL | %ACTIVITYx%-TASKxTOTAL