## Slide 1: Risk Management Plan
PRACTICAL ASSIGNMENT Nº 3
Pablo Almarza
Miguel Arnaiz
Carlos García
S. Xiaofan Fernández
Samai García

## Slide 2: RISK IDENTIFICATION
ID | Name | Risk description | Risk category
R1 | Run out of time | Due to the situation of delivering a project in the same term as a larger one, it can lead to staff relaxation, thus causing the project not to be done in the specified time and leading the company to bankruptcy. | Project risk related to Monitoring and software development. Related to the duration of the project.
R2 | Lack of experience of staff | Since there has been an important increment in technical personnel rotation, programmers of the team may not be familiar with this type of applications nor with the underlying technical architecture used in the department and the solution may not be as good as the client would like. | Technical risk related to personnel management, software development and project conclusion. Related to the quality of the result.
R3 | Budget overrun | As two companies are expected to be subcontracted, UAMSOFT Systems and SOFTCOM, the initial budget could be insufficient and the costs could exceed the initial cost estimations. | Project risk related to the estimation and external sources. Related to the cost of the project.

## Slide 3: RISK ESTIMATION
ID | Name | Likelihood | Justification | Risk impact | Justification
R1 | Run out of time | Low 0.3 | Since the deadline of the project is the same as one 10 times larger, we will be able to finish it on time. | Very high 0.9 | If we, somehow, fail to deliver the work on time, the company will bankrupt.
R2 | Lack of experience of staff | Very high 0.9 | The company has already twice the personnel than expected. This personnel is not qualified as there has been an important rotation in the company. | High 0.8 | If the company personnel is not familiarized with the applications to be used, they will not be able to develop the project with the expected quality and this may end in the dissatisfaction of the client with the final product.
R3 | Budget overrun | High 0.8 | The company is a project away from bankrupt so we assume that the budget is low, so outsourcing to two companies can create budget problems | High 0.8 | If the company costs exceed the budget, this could lead in the need to cut in personnel and this could end in

## Slide 4: RISK ASSESSMENT
ID | Name | Priority | Breaking points
R2 | Lack of experience of staff | Priority = Probability of Occurrence * Probability of Impact = 0.9 * 0.8 = 0.72 | At the end of each increment, unitary tests will be carried out in each module and integration tests for each unit. The breaking point will be when some implementation or integration does not allow the correct execution of the application and is not recoverable.
R3 | Budget overrun | Priority = Probability of Occurrence * Probability of Impact = 0.8 * 0.8 = 0.64 | After each of the milestones established, the budget will be examined, and when the excess is 20% extra of the initial budget, this will be the breaking point.
R1 | Run out of time | Priority = Probability of Occurrence * Probability of Impact = 0.3 * 0.9 = 0.27 | After each of the milestones established in each of the increments, the project time planning will be revised. If we exceed by more than 20% of the established time, a margin of one week will be given to present a new project plan.

## Slide 5: RISK MANAGEMENT - PREVENTIVE ACTIONS
ID | Name | Preventive actions
R1 | Run out of time | Ask for follow-up reports to know how the company is progressing and detect possible delays on time. Clarify in the contract the conditions and delivery dates, as well as the measures our company will take if there is a delay, in this way the client is aware of the conditions from the beginning. Involve all staff in the project so that no one is left behind.
R2 | Lack of experience of staff | As it exists the possibility of personnel rotation, we can ask them to create quality documentation so that future programmers can understand the code. To solve the problem of the team's lack of development experience in this type of applications, motivate them to take additional training courses in the field. Weekly meeting where the project manager can revised the work done and make the necessary adjustments to ensure the quality of the product is the best possible. Good communication between workers and with the project manager.
R3 | Budget overrun | Define milestones. Monitoring the expenses. Require functional products from both external companies in each delivery, to have something functional in the case of budget excess so we can be able to continue developing the product from this point on. Clarify in the contract the conditions and costs as well as measures that our company can take if the budget overrun, so that companies are conscient of these conditions from the beginning.

## Slide 6: RISK MANAGEMENT - CORRECTIVE ACTIONS
ID | Name | Corrective actions
R1 | Run out of time | Contract authorized companies to audit the company or companies that have delayed and find out the causes. Agree with the company a new plan to update the product, analyzing with them the causes of the delay and how to avoid it in the future. Ask for more time in addition to reducing the cost
R2 | Lack of experience of staff | For those workers who do not fully understand the architecture of the system or development of this type of applications, they will be instructed with additional external courses. In order for the inexperienced programmers to understand the work methodology and make them familiar with it, form small groups with veterans and new programmers for instruct them. If the members of the programming team are not able to successfully develop each of the increments, an attempt will be made to hire additional qualified personnel.
R3 | Budget overrun | Readjust the remaining cost and optimize it. Seek for more funding. Reduce the project scope to reduce costs.